## Slide 1
Received
Vendor
Quote
Accounts
GA
PO
WIP
Done
PROJECT PROPOSAL · ICT DIVISION
ICT Printer Upkeep &
Procurement Tracking System
Recommended requirements, open-source technology stack, hosting & team plan — with a live pipeline view so we always know where every request is stuck.
Prepared for: Ministry ICT Management · Date: 9 July 2026 · Status: For Approval

## Slide 2
WHY THIS PROJECT
The problem we are solving
02
Printer repairs & procurement pass through many hands — ICT, vendors, Accounts, General Administration. Today no one can say, at a glance, where a request is stuck.
No single source of truth
Requests tracked in email, spreadsheets and memory.
Invisible bottlenecks
Weeks lost waiting on a quote or an approval — noticed too late.
No audit trail
Who changed what, and when? Hard to answer, easy to dispute.
No reporting
Cost, vendor performance and repair times are guesswork.
THE OBJECTIVE
Know exactly where every printer request is in the process, at all times — and see it stall before it becomes a problem.

## Slide 3
THE SOLUTION
One system, the whole lifecycle
03
A single web application that follows a request from intake to close, with a visual pipeline everyone can read.
Pipeline view
Colour-coded stage tracker on every ticket — and a division-wide board — so blockages are obvious.
Admin dashboard
Pending vs completed counters, average completion time, and graphs by month, department & vendor.
Full audit log
Every change records old value, new value, who and when — nothing overwritten.
Asset register
Owned & leased printers, warranty, maintenance history — ready to grow into full ICT asset mgmt.
Approvals built in
Quotations, requisitions, Accounts & GA sign-off, purchase orders — all in one flow.
Everything exports
CSV, Excel, PDF, JSON — data is portable into any future enterprise system.

## Slide 4
SCOPE
Recommended requirements
04
FUNCTIONAL
Ticket intake — dropdown-driven form, auto ticket numbers
Workflow stages — 13-stage lifecycle, forward & backward moves
Pipeline / process view — for all users (see slide 07)
Approvals — Quotation → Requisition → Accounts → GA → PO
Printer register — owned/leased, warranty, service history
Vendors & departments — CRUD with duplicate prevention
Reports & exports — CSV / Excel / PDF / JSON
NON-FUNCTIONAL
Role-based access — Admin · ICT Officer · Viewer
Audit logging — every field change, immutable
Dashboard & graphs — pending vs completed, trends
Attachments — quotes, delivery notes (20 MB default)
Responsive web — desktop-first, dark & light mode
Data portability — no lock-in; standard formats
Future-ready — SSO/OIDC hook, extend to other assets

## Slide 5
ARCHITECTURE
Recommended stack — 100% open-source
05
LAYER
TECHNOLOGY
LICENSE
LICENSE COST
Frontend
Flutter (Material 3) + Riverpod
BSD-3
$0
Backend API
Node.js 22 + TypeScript, Express
MIT
$0
Database
PostgreSQL 16
PostgreSQL Lic.
$0
Web server
nginx
BSD-2
$0
Auth
JWT (SSO/OIDC-ready)
MIT
$0
Packaging
Docker + Docker Compose (Engine CE)
Apache-2.0
$0
Operating system
Ubuntu Server LTS
Free / GPL
$0
TLS certificate
Let's Encrypt / internal CA
Free
$0
Total recurring software-licensing cost: $0 — no per-seat fees, no vendor lock-in, no renewal surprises.

## Slide 6
RATIONALE
Why this stack is the right call
06
No licensing cost, ever
Every component is free and open-source — budget goes to people and hosting, not licences.
No vendor lock-in
Open standards and plain-SQL data mean we can move hosts or export everything at any time.
Runs entirely on-premise
Fits the ministry's own servers and network policy — data never has to leave the building.
Small, boring, proven
PostgreSQL, Node and nginx run a huge share of the internet — easy to hire for and support.
One command to deploy
Docker Compose brings up the whole stack; migrations run automatically on start.
Grows with us
Same codebase extends from printers to full ICT asset management — no rewrite.

## Slide 7
FLAGSHIP FEATURE
Pipeline view — see where it's stuck
07
A live board of every stage with a count of tickets waiting there. Bottlenecks light up in amber/red so we act immediately.
2
Received
3
Vendor Contacted
5
Quotation
2
Requisition
7
Accounts
4
GA Approval
1
PO Issued
3
Vendor WIP
6
Completed
BOTTLENECK
Done / healthy
Current / moving
Waiting
Stuck / blocked
Available to everyone, not just admins. Only ICT staff use this system, so every signed-in user sees the pipeline and can flag a stall — no gatekeeping the one view that prevents delays.

## Slide 8
ADMIN DASHBOARD
Pending vs completed, with graphs
08
23
OPEN / PENDING
41
COMPLETED (MO.)
6.4 d
AVG. COMPLETION
3
BLOCKED
Chart: Pending vs Completed
| Completed | Pending | Blocked
Tickets | 41 | 23 | 3
Chart: Monthly requests — received vs completed
| Feb | Mar | Apr | May | Jun | Jul
Received | 28 | 34 | 30 | 39 | 44 | 36
Completed | 25 | 31 | 29 | 35 | 41 | 33

## Slide 9
ACCOUNTABILITY
Audit logs — who changed what, when
09
Every create, update and stage change writes an immutable row: entity, field, old value, new value, user and timestamp. Nothing is ever overwritten — the full history is always recoverable.
— Field-level diffs one row per changed field
— Filterable by entity, user or date, from the admin dashboard
— Immutable history is append-only, never edited
— Recent-activity feed live stream on the dashboard
AUDIT LOG
09:14
A. Mwangi
Ticket ICT-2026-000142 stage → Sent to Accounts
09:02
J. Otieno
Quotation amount 1,200 → 1,150
08:47
A. Mwangi
Ticket ICT-2026-000141 vendor → PrintCare Ltd
08:31
S. Kamau
Printer P-0087 status active → repair
Yest.
J. Otieno
Requisition REQ-2026-0031 created
Yest.
Admin
User b.achieng role Viewer → ICT Officer

## Slide 10
INFRASTRUCTURE
Hosting requirements (internal)
10
Small workload — up to ~25 ICT users. One modest VM runs all three containers (PostgreSQL + API + web). No GPU, cache or message queue.
Minimum
works
CPU
2 vCPU
RAM
4 GB
Disk
40 GB SSD
OS
Linux + Docker
Network
100 Mbps LAN
Recommended
comfort
CPU
4 vCPU
RAM
8 GB
Disk
100 GB SSD
OS
Ubuntu LTS
Backups
nightly
What it needs
— Two Docker volumes to back up: database + attachments
— Nightly pg_dump + volume copy (cron)
— TLS terminated at existing reverse proxy / load balancer
— Health endpoint for uptime monitoring
— ~1 GB storage per 1,000 attachments

## Slide 11
COSTING 1 OF 2
Software & licensing — the easy part
11
$0
recurring software &
licensing cost
Flutter, Node.js, PostgreSQL, nginx, Docker and Linux are all free & open-source. No per-seat fees. No renewals.
COMPONENT
LICENSE
COST
Flutter (frontend framework)
BSD-3-Clause
$0
Node.js + TypeScript (backend)
MIT / Apache
$0
PostgreSQL 16 (database)
PostgreSQL License
$0
nginx (web server)
BSD-2-Clause
$0
Docker Engine CE + Compose
Apache-2.0
$0
Ubuntu Server LTS
Free
$0
Let's Encrypt TLS
Free
$0
All app libraries (Riverpod, zod…)
MIT / BSD
$0
TOTAL — software licensing
$0

## Slide 12
COSTING 2 OF 2
Where the real budget goes
12
Cost is people and hosting, not licences. Indicative figures — apply local rates; on-prem on existing hardware is close to zero marginal cost.
Internal hosting (recommended)
≈ $0–600 / yr
— On existing hypervisor 1 VM = chargeback only, often ~$0
— If a new small server ~$40–50/mo cloud-equiv.
— Backups existing ministry backup — negligible
— TLS Let's Encrypt / internal CA — free
Build (one-time)
3–4 mo delivery
— Effort ~2–3 developers, part-time BA & QA
— Cost driver personnel only — apply local rates
— Deliverable deployed system + docs + handover
— Basis codebase already substantially built
Run & maintain
≈ 0.25 FTE
— Ongoing 1 person part-time
— Work updates, backups check, small changes
— Tooling free — same open-source stack
— Scale grows to full ITSM, no new licences

## Slide 13
RESOURCING
Team — how many people
13
Lean by design. Minimum viable team of 2; recommended 3–4 for comfortable delivery and QA. Roles can double up.
Project Lead / BA
Requirements, stakeholder sign-off, UAT coordination
0.5 FTE
Backend Developer
Node/TypeScript API, PostgreSQL, workflow & audit logic
1.0 FTE
Flutter Developer
Web UI, pipeline & dashboard, charts (can be full-stack)
1.0 FTE
QA / Tester
Test cases, UAT, data validation
0.5 FTE
DevOps (part-time)
Docker deployment, backups, TLS — often the same backend dev
0.25 FTE
Headcount
2 min
3–4
recommended
≈ 3.25 FTE peak during build, dropping to 0.25 FTE to run.

## Slide 14
DELIVERY
Phased rollout
14
Phase 1 · Weeks 1–2
Setup & sign-off
Confirm requirements, provision VM, deploy skeleton stack
Phase 2 · Weeks 3–7
Core build
Tickets, workflow pipeline, approvals, printer & vendor registers
Phase 3 · Weeks 8–10
Dashboard & audit
Pending/completed graphs, audit log, reports & exports
Phase 4 · Weeks 11–13
UAT & go-live
User testing, training, data import, production cutover
Indicative — ~3 months to production. The existing codebase means Phase 2 starts from a working base, not a blank page.

## Slide 15
RECOMMENDATION
Approve build on the open-source stack
100% open-source
$0 in software licences — Flutter, Node, PostgreSQL, Docker, Linux.
Runs on our own servers
One modest VM; data never leaves the ministry.
Pipeline for everyone
Every ICT user sees where a request is stuck — fixed fast.
Audit & dashboard
Pending vs completed, graphs, and a full immutable trail.
Lean team
2 minimum, 3–4 recommended; ~3 months to go-live.
Low run cost
≈ 0.25 FTE and near-zero hosting to keep it running.
Next step: sign-off to begin Phase 1 — provisioning and requirements confirmation.